## Checklist
Software QA Checklist
Project Name |  | Todo application
Tester Name |  | Mohamed Hussien
Software Version |  | V 1.0
Date |  | 2024-05-03
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Status
TC_001 | Signup | Signup should not be possible with an empty first name | To be in the signup page | 1- Keep the first name empty. 2- Fill a correct last name. 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Keep empy 2- Last name: hussien 3- temail: test@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should show this error "First Name is required, and it should be more than 3 characters" | This error message was displayed "First Name is required, and it should be more than 3 characters" | PASS
TC_002 | Signup | Signup should not be possible with a name with 2 characters | To be in the signup page | 1- Enter a first name with two characters 2- Fill a correct last name. 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Mo 2- Last name: Hussien 3- temail: test1@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should show this error "First Name is required, and it should be more than 3 characters" | This error message was displayed "First Name is required, and it should be more than 3 characters" | PASS
TC_003 | Signup | Signup should be posible if the first name is equal to 3 characters | To be in the signup page | 1- Enter a first name with three characters. 2- Fill a correct last name. 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Moh 2- Last name: Hussien 3- temail: test2@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should signup the user correctly | This error message was displayed "First Name is required, and it should be more than 3 characters" | FAIL
TC_004 | Signup | Signup should be posible if the first name is equal to 4 characters | To be in the signup page | 1- Enter a first name with four characters 2- Fill a correct last name. 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Moha 2- Last name: hussien 3- temail: test3@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should signup the user correctly | Signup was correct | PASS
TC_005 | Signup | Signup should not be possible with an empty last name | To be in the signup page | 1- Fill a correct first name. 2- keep last name empty 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Mohamed 2- Last name: empty 3- temail: test@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should show this error "last Name is required, and it should be more than 3 characters" | It showed the correct error | PASS
TC_006 | Signup | Signup should not be possible with a last name with 2 characters | To be in the signup page | 1- Fill a correct first name. 2- Fill last name with 2 characters 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Mohamed 2- Last name: Hu 3- temail: test1@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should show this error "last Name is required, and it should be more than 3 characters" | It showed the correct error | PASS
TC_007 | Signup | Signup should be posible if the last name is equal to 3 characters | To be in the signup page | 1- Fill a correct first name. 2- Fill last name with 3 characters 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Mohamed 2- Last name: Hus 3- temail: test2@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should signup the user correctly | The signup was correct | PASS
TC_008 | Signup | Signup should be posible if the last is equal to 4 characters | To be in the signup page | 1- Fill a correct first name. 2- Fill last name with 4 characters 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Mohamed 2- Last name: Huss 3- temail: test3@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Should signup the user correctly | The signup was correct | PASS
TC_009 | Signup | Signup should not be possible if the email is invalid | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill a wrong email formate 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Mohamed 2- Last name: Hussien 3- temail: test3@.com 4- password: Test123! 5- confirm password: Test123! | Signup should fail | Signup failed | PASS
TC_010 | Signup | Signup should not be possible if the email is empty | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill an empty email 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Mohamed 2- Last name: hussien 3- temail: tempty email 4- password: Test123! 5- confirm password: Test123! | Signup should fail | Signup Failed | PASS
TC_011 | Signup | Signup should not be possible if the email is exisit is the database | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill an email that is already registered in the database 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Mohamed 2- Last name: Hussien 3- temail: me@mohamed123.com 4- password: Test123! 5- confirm password: Test123! | Signup should fail | Signup Failed | PASS
TC_012 | Signup | Signup should be possible if the email is correct and not registered in the database | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill a correct email that is not registered in the database 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name: Mohamed 2- Last name: hussien 3- temail: test3@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Signup should work correctly | Signup was successfull | PASS
TC_013 | Signup | Signup should fail if the password is not in a valid formate | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill a correct email 4- Fill a not correct password. 5- Fill a correct confirm password. 6- Click on signup button | 1- First name:Mohamed 2- Last name: hussien 3- temail: test4@gmail.com. 4- password:Test1234 5- confirm password: Test123! | Signup should fail | Signup Failed | PASS
TC_014 | Signup | Signup should fail if the confirm password is not in a valid formate | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill a correct email 4- Fill a correct password. 5- Fill a not correct confirm password. 6- Click on signup button | 1- First name: Mohamed 2- Last name: hussien 3- temail: test4@gmail.com. 4- password: Test123! 5- confirm password: Test1234 | Signup should fail | Signup Failed | PASS
TC_015 | Signup | Signup should fail if both the password are in a good formate but not equal to each other | To be in the signup page | 1- Fill a correct first name. 2- Fill la correct last name. 3- Fill a correct email 4- Fill a correct password. 5- Fill a correct confirm password but not equal to the password. 6- Click on signup button | 1- First name: Mohamed 2- Last name: hussien 3- email: test3@gmail.com. 4- password: Test123! 5- confirm password: Test123!! | Signup should fail | Signup Failed | PASS
TC_016 | Signup | Signup should work correctly if the two passwords are in a correct formate and equal to each other | To be in the signup page | 1- Fill a correct first name. 2- Fill a correct last name. 3- Fill a correct email 4- Fill a correct password. 5- Fill a correct confirm password that is equal to the password. 6- Click on signup button | 1- First name: Mohamed 2- Last name: Hussien 3- email: test3@gmail.com. 4- password: Test123! 5- confirm password: Test123! | Signup should work correctly | Signup is correct | PASS
TC_017 | Login | Login should not be possible if the email is invalid | To be in the Login page | 1- Fill an invalid email. 2- Fill a correct password. 3- Click on login bottun. | 1- email: test@.com. 2- password: Test123! | Login should fail | Login Failed | PASS
TC_018 | Login | Login should not be possible if the email is empty | To be in the Login page | 1- Fill an empty email. 2- Fill a correct password. 3- Click on login bottun. | 1- email:empty 2- password: Test123! | Login should fail | Login Failed | PASS
TC_019 | Login | Login should be possible if the email is correct and registered in the database and password is correct | To be in the Login page | 1- Fill a correct and registerd email. 2- Fill a correct password. 3- Click on login bottun. | 1- email: test3@gmail.com. 2- password: Test123! | Login should work correctly | Login worked correctly | PASS
TC_020 | Login | Login should not be possible if the email is correct and not registered in the database | To be in the Login page | 1- Fill a correct and unregisterd email. 2- Fill a correct password. 3- Click on login bottun. | 1- email: ali@gmail.com. 2- password: Test123! | Login should fail | Login Failed | PASS
TC_021 | Login | Login should fail if the email is correct and password is empty | To be in the Login page | 1- Fill a correct email. 2-Keep the password empty. 3- Click on login bottun. | 1- email: test3@gmail.com. 2- password: empty | Login should fail | Login Failed | PASS
TC_022 | Login | Login should fail if the email is correct and password is not correct | To be in the Login page | 1- Fill a correct email. 2-Fill a wrong password. 3- Click on login bottun. | 1- email: test3@gmail.com. 2- password:test4562 | Login should fail | Login Failed | PASS
TC_023 | Login | while logging in the lodar sign should be in the center | To be in the Login page | 1- Fill a correct email. 2-Fill a correct password. 3- Click on login bottun. | 1- email: test3@gmail.com. 2- password:Test123! | The lodar sign should be in the center | The lodar sign is in the right | FAIL
TC_024 | Todo | creat a new todo | to be in the todo page | 1- Fill a correct email 2- Fill a correct password. 3- Click on login bottun. | 1- Todo name : Task1 | A new todo should be created | An error message appears: "forbeddin to access this resource" | FAIL
Note on A6: A unique number for each test case
Note on B6: The test module, feature, condition, that can be divided into test cases
Note on C6: A short description of the test case, Anyone should be able to understand what we are going to test while reading it.
Note on D6: Any pre steps needed to start the test
Note on E6: The steps that we need to execute to do the test
Note on F6: The data that we are going to use while doing the steps
Note on G6: What is the expected output from the test
Note on H6: What is the expected output from the test

## Bug Report
Defect Report |  | Defect Report |  | Defect Report
Release | V.1.0 | Release | V.1.0 | Release | V.1.0
Title | User is not able to signup if he/she enters a first name with three charachters | Title | The location of the loader in the login page is wrong | Title | "forbidden access to this resource" message will appear when adding a new todo
Description | It happens in all the browsers and all the screen views, the first name that we used during the testing is Moh | Description | After logging and while waiting the response from the server, the loader will appear in a wrong location, down with alot of margin | Description | In the todo page and when you add a new todo, the message "forbidden access to this resource" will appear
Steps | 1- Enter a first name with "Moh". 2- Fill a correct last name."Hussien" 3- Fill a correct email formate, and the email should not be registered in the database. 4- Fill a correct password. 5- Fill a correct confirm password. 6- Click on signup button | Steps | 1- Go to login page 2- Fill the email 3- Fill the password 4- Click on login 5- Check the loader | Steps | 1- Go to Todos Page 2- Creat a new todo
Expected Results | Should be able to signup correctly | Expected Results | The loader should appear correctly in the correct location | Expected Results | Should add a new todo
Actual Result | This error message was displayed "First Name is required, and it should be more than 3 characters" | Actual Result | The loader will be displayed in a wrong location | Actual Result | forbidden access to this resource
Environment | Microsoft edge V.122.0.2365.80 | Environment | Microsoft edge V.122.0.2365.80 | Environment | Microsoft edge V.122.0.2365.80
Screenshot / Video | #VALUE! | Screenshot / Video | #VALUE! | Screenshot / Video | #VALUE!
Rate | 2022-05-05 | Rate | 2022-05-05 | Rate | 2022-05-05
Priority | B | Priority | C | Priority | A
Status | Open | Status | Open | Status | Open

## ID (hidden)
Software QA Checklist
Project Name
Tester Name
Software Version
Date
ID | Test Suite | Test Title | Pre-Condition | Test Steps | Test Data | Expected result | Actual Result | Status
TC_001
TC_002
TC_003
Test case ID : is a unique number for each test case
© Copy rights for QAcart 2022

## Status (hidden)
PASS
FAIL
N/A
N/E